## PDCA Register
PDCA REGISTER
[8 empty] | ACT | PLAN |  |  | Total | Critical | High | Moderate | Low | Negligible
[8 empty] | 0% | 100% |  | Risk | 0 | 0 | 0 | 0 | 0 | 0
| PROJECT | Reduce time spent waiting for lab results | LEADER |  | CYCLE # | 1 |  | 0% | 81.67% |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
| PROCESS | Molecular testing | PREPARED BY |  | UPDATED |  |  | CHECK | DO |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
| Select … | What? | Who? | When? | Expected in hours | % | Open/Closed |  |  |  |  | 0 |  |  |  |  | 0
[5 empty] | 153 | 40.31%
| PDCA PHASE | ACTIVITY | OWNER | DUE DATE | ACTIVITY TIME | COMPLETION % | STATUS | LESSONS LEARNED
1 | PLAN | Explore all available information | Team |  | 4 | 100% | CLOSED |  |  | PLAN
2 | PLAN | Brainstorm and generate solution ideas | Team |  | 8 | 100% | CLOSED |  |  | DO
3 | PLAN | Select the most promising solution | Team |  | 4 | 100% | CLOSED |  |  | CHECK
4 | PLAN | Develop an action plan to implement the selected solution | Sami |  | 4 | 100% | CLOSED |  |  | ACT
5 | DO | Perform the steps defined in the action plan | Chadi |  | 32 | 100% | CLOSED
6 | DO | Collect data on the time spent waiting for results | Chadi |  | 6 | 100% | CLOSED |  |  | OPEN
7 | DO | Collect feedback from sample customers | Peter |  | 12 | 45% | OPEN |  |  | CLOSED
8 | CHECK | Analyze data and customer feedback | Sara |  | 8 | 0% | OPEN
9 | CHECK | Assess whether the solution solves the problem | Team |  | 4 | 0% | OPEN
10 | CHECK | Share results with key stakeholders | Sami |  | 2 | 0% | OPEN
11 | CHECK | Discuss further improvements and quick wins | Team |  | 4 | 0% | OPEN
12 | ACT | Develop an implementation plan | Sami |  | 6 | 0% | OPEN
13 | ACT | Implement the solution in full-scale | Chadi |  | 40 | 0% | OPEN
14 | ACT | Document and measure the results obtained | Sami |  | 4 | 0% | OPEN
15 | ACT | Develop standard operating procedures | Zakaria |  | 3 | 0% | OPEN
16 | ACT | Train employees on the new process | Sara |  | 12 | 0% | OPEN
17
18
19
20
21
22
23
24
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This PDCA template supports the application of the PDCA model in problem-solving and project management. It is a user-friendly tool for planning and tracking activities across each PDCA phase. Key activities can be listed, with assigned owners, due dates, progress tracking, and lessons learned. It includes a simple dashboard that shows progress and keeps the team and stakeholders informed. |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | At the beginning of the project, enter the project title and other key details in the top section of the template.
2 | Under each PDCA phase — Plan, Do, Check, Act — list the relevant activities. |  | LEARN MORE
3 | For each activity, specify the responsible owner and the due date. |  | Version Number: 3.1
4 | As the project moves forward, regularly update the template.
5 | Record completion rates and make any necessary changes. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
6 | After each activity, document insights and lessons learned to guide future improvements. |  | info@citoolkit.com
7 | The PDCA model is continuous. Once a cycle is complete, begin a new one to drive ongoing improvement.
8 | Note: Only the white cells are intended for user input. |  | To learn more about other continuous improvement tools, visit the Citoolkit website at:
www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com